## Slide 1
Constraints and Timelines

## Slide 2
December 16 is too late to find out
The demo is Friday, December 18
Two teammates were at Regional all week
The plan assumed everyone, every day
Now the only choice is shipping less
MCCTC | AI Automation & Software Development
Notes: Here is how a sprint dies. Nobody wrote down the limits. The plan assumed four people in the room every day. BPA week happened, which everyone knew about in November, and on December sixteenth the team discovers it has half the time it planned for. At that point there is no decision left, only less. Today you write the limits down while cutting is still a choice.

## Slide 3
A constraint is a fence, not a feature
Technical
Standard library, lab machines, Python 3.14
Time
Acceptance demo Friday, December 18
People
Known BPA days, known absences
Legal and ethical
No personal information, ever
Every constraint comes with why it exists
MCCTC | AI Automation & Software Development
Notes: A requirement is something the program does. A constraint is a fence around where the program is allowed to exist. Technical limits, time limits, people limits, legal and ethical limits, and whatever the stakeholder cannot bend on. Every one you write down needs a reason next to it. A constraint with a reason can be questioned or confirmed. A constraint without one is a rumor.

## Slide 4
The language is a constraint too
Python: reads and validates files, testable, runs here
Spreadsheet: stakeholder knows it, but breaks silently
JavaScript page: shareable, but nobody here knows it yet
Choosing Python is a decision. Log the reason.
MCCTC | AI Automation & Software Development
Notes: You are building in Python, and I want you to be able to say why, because a stakeholder might ask. Python reads and checks messy files, you can test it, and it runs on these machines. A spreadsheet is what many stakeholders already use, and one dragged formula can break it without a sound. A web page can be shared with one link, and none of you has learned it yet. For this sprint Python wins, and that is a decision with reasons, so it goes in your decision log.

## Slide 5
Count class days, not calendar days
class_days = [
"Mon Nov 30", "Tue Dec 1", "Wed Dec 2", "Thu Dec 3", "Fri Dec 4",
"Mon Dec 7", "Tue Dec 8", "Wed Dec 9", "Thu Dec 10", "Fri Dec 11",
"Mon Dec 14", "Tue Dec 15", "Wed Dec 16", "Thu Dec 17", "Fri Dec 18",
]
bpa_days = ["Mon Dec 7", "Tue Dec 8", "Wed Dec 9", "Fri Dec 11"]
here = 0
for day in class_days:
if day not in bpa_days:
here = here + 1
print("Days a competitor is in the room:", here)
MCCTC | AI Automation & Software Development
Notes: Timelines run on class days, because weekends and winter break do not build software. Here is our sprint as a list. The BPA days are the ones a competitor might miss, worst case. The loop counts the days that are not BPA days. It prints eleven. Fifteen days in the sprint, eleven in the room. Plan for the worst case on paper.

## Slide 6
Plan backward from what cannot move
1
Acceptance tests agreed
Eleven class days before demo
2
First working increment
Five class days before demo
3
Baseline
Two class days before demo
4
Demo date
Fixed. Start there.
MCCTC | AI Automation & Software Development
Notes: Do not plan forward from today, because forward planning always runs out of days at the end. Start at the date that cannot move, Friday the eighteenth, and count back in class days. Two class days back is Wednesday the sixteenth, the baseline. Five back is Friday the eleventh, the first increment. Eleven back is Thursday the third, which is tomorrow, when your acceptance tests get written.

## Slide 7
Does the work fit
remaining_estimate = 22
days_left = 6
blocks_per_day = 2
people = 3
absences = 4
capacity = days_left * blocks_per_day * people - absences
print("Capacity:", capacity, "Remaining:", remaining_estimate)
if remaining_estimate > capacity:
print("Cut scope now.")
else:
print("Fits, with", capacity - remaining_estimate, "blocks of slack.")
MCCTC | AI Automation & Software Development
Notes: Capacity is the build time you really have. Days, times blocks per day, times people, minus the blocks you already know you will lose. Six days, two blocks, three people, minus four for BPA. Thirty two blocks. The work is estimated at twenty two, so it fits with ten blocks of slack. That slack is not wasted. Estimates are guesses and guesses run low. Slack is what absorbs the bug that eats a whole afternoon.

## Slide 8
Watch this
# Copied from the BPA schedule email.
bpa_days = ["Mon Dec 07", "Tue Dec 08", "Wed Dec 09", "Fri Dec 11"]
here = 0
for day in class_days:
if day not in bpa_days:
here = here + 1
print("Days a competitor is in the room:", here)
MCCTC | AI Automation & Software Development
Notes: Same program. This time a teammate copies the BPA dates straight out of the official schedule email, which writes the dates its own way. Everything else is identical. Predict the number before I run it.

## Slide 9
Three days that do not exist
Days a competitor is in the room: 14
MCCTC | AI Automation & Software Development
Notes: No error. Fourteen instead of eleven. Mon Dec zero seven and Mon Dec seven are different strings, so not in is True for every BPA day except Friday, which happened to be written the same way. The plan gains three days that do not exist, capacity looks comfortable, and the team promises more than it can build. A comfortable number stops the questions, which is why this bug survives. Print the list of days you excluded and read it.

## Slide 10
A milestone you can check
A date on a class day
One named owner, plus a backup
Done when: something a stranger could verify
Tested checks passing, not percent complete
MCCTC | AI Automation & Software Development
Notes: Every milestone on your timeline needs three things. A class day. One owner, with the backup from your charter. And a done when that a stranger could check. Tests written and failing is checkable. Eighty percent done is not, because nobody can check a percent. When in doubt, make the done when a number of acceptance checks passing.

## Slide 11
What you are about to build
Build 1
Constraints, each with its reason
Build 1
A baseline measurement from real sample data
Build 2
A timeline on class days, including BPA week
Build 2
Capacity counted, and what you cut first if it shrinks
MCCTC | AI Automation & Software Development
Notes: Build one, list every constraint with why it exists, then take a baseline measurement. Count something real in your stakeholder's sample data, like how many rows have a problem nobody would catch today. That number is what Measure means. Build two, your timeline on class days, with BPA week and every known absence in it. Count capacity. Then write down what you will cut first if capacity shrinks, and write it today, while nobody is panicking.